## 1. Executive Overview
ENDevo SaaS Platform - Complete Technical & Project Plan
Project Details
Project Name | ENDevo SaaS MVP - End-of-Life Readiness Platform
Timeline | February 2 - March 30, 2026 (8 weeks MVP)
Team | Nermeen (backend + DevOps) + 1 Frontend Developer
Development Cost | $30-40K
Infrastructure Cost | $5-7K (covered by $100K AWS credits)
Target Revenue Y1 | ~$50,000 ARR
First Customer | March 30, 2026
3 Customers | May 15, 2026
$10K/Month ARR | May 15, 2026

## 2. Architecture Overview
HIGH-LEVEL SYSTEM ARCHITECTURE
┌─────────────────────────────────────────────────────────────────────────────┐ │ ENDEVO SAAS PLATFORM │ │ 4-TIER SERVERLESS ARCHITECTURE │ └─────────────────────────────────────────────────────────────────────────────┘ TIER 1: CLIENT LAYER ┌──────────────────────────────────────────────────────────────────────────┐ │ React 19 + TypeScript + Vite (Vercel CDN) │ │ ├─ Employee Dashboard (assessment, learning, checklist, progress) │ │ ├─ HR Admin Dashboard (aggregated metrics only, NO personal data) │ │ ├─ Auth UI (Cognito login, MFA, password reset) │ │ └─ Learning Modules (6-hour educational content) │ └──────────────────────────────────────────────────────────────────────────┘ │ HTTPS/TLS 1.3 (Encrypted) ▼ TIER 2: API GATEWAY LAYER ┌──────────────────────────────────────────────────────────────────────────┐ │ AWS API Gateway (HTTP API) │ │ ├─ Rate Limiting (100 req/min per user) │ │ ├─ CORS Enforcement (app.endevo.life only) │ │ ├─ Request Validation (Zod schemas) │ │ ├─ JWT Token Validation (every request) │ │ └─ WAF Protection (SQL injection, XSS, DDoS) │ └──────────────────────────────────────────────────────────────────────────┘ │ REST Endpoints (25+) ▼ TIER 3: APPLICATION LOGIC LAYER ┌──────────────────────────────────────────────────────────────────────────┐ │ AWS Lambda (Node.js 22 + Fastify) │ │ ├─ Auth Service (Cognito integration, JWT generation) │ │ ├─ Assessment Engine (questionnaire → risk assessment → checklist) │ │ ├─ Learning Service (module delivery, progress tracking) │ │ ├─ Dashboard Service (employee + HR views) │ │ ├─ Export Service (PDF + JSON generation, S3 upload) │ │ ├─ Email Service (SES notifications, nudges, invites) │ │ └─ Audit Logging (all sensitive actions logged) │ │ │ │ Performance: <100ms avg, <500ms p95 │ │ Scalability: 0 → 10K concurrent users (auto-scaling) │ │ Compute: 1024-2048 MB memory, 30s timeout │ └──────────────────────────────────────────────────────────────────────────┘ │ Database Context Injection SET app.user_id SET app.org_id SET app.user_role ▼ TIER 4: DATA LAYER ┌─────────────────────────────────────────────────────────────────────────┐ │ PostgreSQL 16 RDS (Multi-Tenant with Row-Level Security) │ │ ├─ organizations (tenants/companies) │ │ ├─ users (people + roles) │ │ ├─ assessments (questionnaire responses, risk level) │ │ ├─ modules (learning content - shared) │ │ ├─ progress (user learning progress per module) │ │ ├─ checklists (personalized action items - JSONB) │ │ ├─ org_metrics (aggregated HR dashboard data) │ │ ├─ survey_responses (post-completion feedback) │ │ └─ audit_log (compliance + security trail) │ │ │ │ Security: Row-Level Security (RLS) policies │ │ - HR physically cannot SELECT employee personal data │ │ - Database enforces isolation (not application layer) │ │ - Encryption at rest (KMS) + in transit (TLS) │ │ - Automated backups (daily, 7-day retention) │ └─────────────────────────────────────────────────────────────────────────┘ │ ┌───────────┼───────────┐ ▼ ▼ ▼ ElastiCache Redis S3 + CloudFront AWS Secrets Manager (Sessions, Cache) (PDFs, Exports) (Encrypted Credentials) MONITORING & OBSERVABILITY (Cross-Cutting) ┌────────────────────────────────────────────────────────────────────┐ │ CloudWatch (logs, metrics, alarms) │ │ X-Ray (distributed tracing, service map) │ │ Sentry (error tracking, real-time alerts) │ │ CloudTrail (audit all API calls) │ └────────────────────────────────────────────────────────────────────┘ DEPLOYMENT PIPELINE (CI/CD) ┌────────────────────────────────────────────────────────────────────┐ │ Developer │ │ ↓ (git push) │ │ GitHub (code repository) │ │ ↓ (trigger) │ │ GitHub Actions (test, build, lint) │ │ ↓ (on success) │ │ Vercel (frontend) + AWS Lambda (backend) │ │ ↓ │ │ Production (live for customers) │ └────────────────────────────────────────────────────────────────────┘

## 3. AWS Services Detail
AWS SERVICES - DETAILED SPECIFICATIONS
Service | Purpose | Configuration (MVP) | Cost/Month | SLA | Scaling | Notes
API Gateway | REST API routing, rate limiting, CORS | HTTP API, 100 req/min/user | $3.50 + $0.30/1M | 99.95% | Auto-scale | Cheaper than REST API
Lambda | Serverless compute, business logic | 1024-2048 MB, 30s timeout, Node.js 22 | $15/month (free tier) | 99.99% | Unlimited | Pay per request
RDS PostgreSQL | Multi-tenant database, RLS | db.t3.small, 20 GB storage, Multi-AZ | $200/month (AWS free tier) | 99.95% | Vertical scaling | RLS policies enforced
ElastiCache | Session + query caching | cache.t3.micro, 1 GB | $20/month | 99.95% | Vertical | Improves query speed
S3 | PDF/export storage | 1 GB quota (MVP), encryption | $0-5/month | 99.99% | Unlimited | 100% private access
CloudFront | CDN for S3 + static assets | Edge locations worldwide | $5-10/month | 99.99% | Auto | Geo-distributed
Cognito | User authentication, MFA | User Pool, 1 app client, SMS + TOTP | $5-10/month (free tier) | 99.99% | Unlimited | Handles SSO in Phase 2
SES | Email service | 62.5K emails/month (free tier) | $0-5/month | 99.9% | Unlimited | Notifications + invites
CloudWatch | Logging, metrics, alarms | 5GB free logs, custom metrics | $10-20/month | 99.99% | Unlimited | Real-time monitoring
X-Ray | Distributed tracing | All requests traced | $5/month | 99.99% | Auto | Understand request flow
Secrets Manager | Encrypted credentials | DB password, API keys, JWT secret | $5/month | 99.99% | N/A | Rotate automatically
IAM | Access control, roles | Lambda exec role, RDS access | Included | 100% | N/A | Principle of least privilege
VPC | Network isolation | Lambda in VPC, RDS in subnet | Included | 100% | N/A | Security boundary
KMS | Encryption key management | AWS managed keys | Included (per use) | 99.99% | N/A | Encrypt S3, RDS
CloudTrail | API audit logging | All AWS API calls logged | $5/month | 99.99% | Unlimited | Compliance

## 4. Database & RLS Policies
POSTGRESQL DATABASE SCHEMA & ROW-LEVEL SECURITY
Core Tables (9)
Table Name | Purpose | Key Fields | Sensitive? | RLS Policy | Retention
organizations | Customer companies | id, name, created_at, billing_email | No | Org owner access only | Keep always
users | People in system | id, org_id, email, role, created_at | Low | User owns record, HR admin sees aggregated | Keep always
assessments | Questionnaire responses | id, user_id, org_id, responses (JSONB), risk_level | YES | User owns only (RLS enforced) | 5 years (compliance)
modules | Learning content | id, title, duration, content (JSONB), created_at | No | Public read (all users) | Keep always
progress | Learning completion | id, user_id, module_id, status, time_spent, completed_at | Moderate | User owns, HR sees aggregated | 5 years
checklists | Personalized action items | id, user_id, org_id, items (JSONB), status | YES | User owns only | 2 years
org_metrics | Aggregated dashboard | id, org_id, enrollment_%, completion_%, demographics | No (aggregated) | HR admin + org owner | Keep always
survey_responses | Feedback + NPS | id, user_id, nps, feedback, created_at | Moderate | User owns, HR sees aggregated only | 2 years
audit_log | Compliance trail | id, user_id, action, resource, timestamp, changes | High | System admin + org owner only | 7 years (compliance)
Row-Level Security (RLS) Policies
Policy Name | Table | Role(s) Affected | Rule | Enforcement
employee_assessments_select_own | assessments | Employee | SELECT own records only (user_id match) | Row-level
employee_progress_select_own | progress | Employee | SELECT/UPDATE own progress only | Row-level
hr_admin_aggregated_view | org_metrics | HR Admin | SELECT aggregated data (org_id match) | Row-level
hr_admin_no_personal_data | assessments, checklists | HR Admin | Deny access to personal data | Row-level
org_owner_full_access | All tables | Org Owner | SELECT all org data (except other orgs) | Row-level
audit_log_restricted | audit_log | System Admin | SELECT only (immutable, append-only) | Row-level

## 5. Project Plan - Phase 1
PHASE 1 MVP - COMPLETE PROJECT PLAN (8 WEEKS)
Week | Focus Area | Tasks (Detailed) | Owner | Hours | Deliverable | Success Criteria
Week 1 (Feb 2-8) | Foundation | AWS account, GitHub org, RDS/Redis, Cognito, CloudWatch, local dev env | Nermeen | 40-50 | Infrastructure live | All services responding
Week 2 (Feb 9-15) | Database | Schema creation, RLS policies, migrations, seed data | Nermeen | 50-60 | DB ready | RLS policies tested + working
Week 3 (Feb 16-22) | Backend P1 | Auth (signup/login), Assessment (create/get/update/results) | Nermeen | 60 | Core endpoints | Unit tests 80%+
Week 4 (Feb 23-Mar 1) | Backend P2 | Learning (modules, progress), Dashboard (employee/HR), Email | Nermeen | 60-80 | All endpoints | Integration tests pass
Week 5 (Mar 2-8) | Frontend P1 | Auth UI, Assessment UI, Learning UI component library | FE Dev | 60-70 | UI components | All forms functional
Week 6 (Mar 9-15) | Frontend P2 | Dashboards (employee + HR), Checklist, Export, responsiveness | FE Dev | 70-80 | Full UI | All pages responsive
Week 7 (Mar 16-22) | Integration | Connect frontend ↔ backend, E2E tests, performance tuning, security audit | Both | 80-100 | Beta release | p95 latency <500ms
Week 8 (Mar 23-30) | Production | Deploy staging/prod, documentation, team training, customer onboard | Both | 60-80 | Live SaaS | First customer happy

## 6. SLA & Performance
SERVICE LEVEL AGREEMENTS & PERFORMANCE TARGETS
Service | AWS SLA | Our Target | Measurement | Monitoring Tool | Alert Threshold | Recovery Action
API Gateway | 99.95% | 99.9% | Uptime (response/second) | CloudWatch | Failures >1%/5min | Auto-scale Lambda
Lambda | 99.99% | 99.9% | Request success rate | CloudWatch | Errors >0.5% | Check logs via Sentry
RDS PostgreSQL | 99.95% | 99.5% | Database availability | CloudWatch | Down >5min | Failover to standby
ElastiCache | 99.95% | 99.5% | Cache availability | CloudWatch | Down >5min | Recreate cluster
Cognito | 99.99% | 99.9% | Auth service availability | CloudWatch | Auth failures >1% | Fallback to JWT
S3 | 99.99% | 99.9% | Object availability | CloudWatch | Upload fails >1% | Retry with exponential backoff
CloudFront | 99.99% | 99.9% | CDN availability | CloudWatch | Cache hit ratio <80% | Purge cache + refresh
Performance Targets
Metric | Target | Tool | Alert | Optimization
First Contentful Paint (FCP) | <1.5s | Lighthouse | >2s | Code splitting, image optimization
Largest Contentful Paint (LCP) | <2.5s | Lighthouse | >3s | Lazy loading, CDN caching
Time to Interactive (TTI) | <3.5s | Lighthouse | >4s | Async JS, reduce main thread work
API Latency (p50) | <100ms | X-Ray | >150ms | Query optimization, Redis cache
API Latency (p95) | <500ms | X-Ray | >750ms | Database indexing, connection pooling
API Latency (p99) | <2s | X-Ray | >3s | Circuit breaker, fallback
Database Query Time (p95) | <50ms | RDS Metrics | >100ms | Index, query plan analysis
Cache Hit Ratio | >80% | Redis Stats | <70% | Cache warming, TTL tuning

## 7. Complete User Workflows
COMPLETE USER WORKFLOWS & INTERACTIONS
Workflow 1: Employee Onboarding
Step 1: Invitation - HR sends invite email (via SES) - Employee clicks link: https://app.endevo.life/invite/[token] Step 2: Signup - Employee enters: email, name, password - Cognito creates account + MFA (SMS/TOTP optional) Step 3: Assessment - Employee answers 15-minute questionnaire - Assessment stored in assessments table (JSONB) - RLS: Only this user can see their response Step 4: Risk Assessment Results - Lambda calculates risk_level (LOW, MEDIUM, HIGH, CRITICAL) - Based on: beneficiaries, will, estate planning, digital legacy - Generates personalized checklist (checklists table, JSONB) Step 5: Learning Journey - Employee sees 6 modules (6 hours content) - Progress tracked per module (progress table) - Can take at own pace (days/weeks) Step 6: Checklist Management - Employee sees personalized TODO items - Marks items complete: Will, Trust, Beneficiaries, Digital Legacy, etc. - System nudges via email (SES) if inactive 7+ days Step 7: Export - Employee can export: Assessment results + Checklist as PDF - PDF generated via Lambda, stored in S3 - Pre-signed S3 URL sent to employee (24-hour expiry) Step 8: Data Portability - Employee can download: Full JSON of all their data - When they leave job: Data remains accessible (no lock-in)
Workflow 2: HR Administrator Dashboard
Step 1: Login - HR admin logs in: email + password (Cognito) - Lambda sets: app.user_id, app.org_id='ACME', app.user_role='hr_admin' Step 2: Dashboard Load - Frontend requests: GET /dashboard/hr - RLS policy: Only return org_metrics where org_id='ACME' - Employee personal data is BLOCKED by database (RLS enforced) Step 3: View Metrics (Aggregated ONLY) - Enrollment: 45% of employees started assessment - Completion: 28% completed full learning journey - Demographics: Age range (20-30: 15%, 30-40: 25%, 40+: 5%) - Average time spent: 3.2 hours per employee Step 4: Encouragement Campaign - HR clicks "Send Nudge" to incomplete employees - Lambda generates email: "Only 2 hours left!" - Sent via SES (no personal data exposed, just reminder) Step 5: Export Report - HR requests: Export org metrics to CSV - Lambda queries org_metrics, generates file - Includes: enrollment %, completion %, demographics, NPS CRITICAL: HR can NEVER see - Individual employee names linked to progress - Assessment responses (personal financial/family info) - Checklist items (which estate planning gaps they have) - Who specifically hasn't completed (privacy preserved)

## 8. Complete Security Posture
COMPREHENSIVE SECURITY & COMPLIANCE ARCHITECTURE
Layer 1: Transport Security
HTTPS/TLS 1.3 | All traffic encrypted | AWS Certificate Manager (free) | Mandatory
CORS Policy | Only app.endevo.life + endevo.life | API Gateway | Strict
Security Headers | CSP, X-Frame-Options, HSTS | API middleware | Enforced
Layer 2: Authentication
Cognito User Pool | Email/password + MFA (SMS/TOTP) | AWS Cognito | Required
JWT Tokens | Signed + expiring (1 hour) | Fastify middleware | Validated on every request
Session Security | HttpOnly cookies, Secure flag | Cognito + Redis | Enforced
Layer 3: Authorization
Role-Based Access Control | employee, hr_admin, org_owner | JWT claims | Strict
Row-Level Security (RLS) | Database enforces tenant isolation | PostgreSQL policies | Database-level
Least Privilege IAM | Lambda role limited to needed services | AWS IAM | Enforced
Layer 4: Data Protection
Encryption at Rest | KMS encryption for S3, RDS | AWS KMS (managed) | Standard
Secrets Management | DB password in Secrets Manager | AWS Secrets Manager | Rotatable
Data Classification | Sensitive fields tagged | Code + docs | Tracked
Layer 5: Application Security
Input Validation | Zod schemas on all endpoints | Fastify middleware | Strict
SQL Injection Prevention | Parameterized queries + RLS | Knex.js + DB policies | Enforced
XSS Prevention | React sanitization + CSP headers | React 19 + headers | Enforced
CSRF Protection | SameSite cookies + token validation | Cognito + middleware | Enforced
Layer 6: Monitoring & Audit
Audit Logging | All sensitive actions logged | audit_log table + CloudTrail | Immutable
Real-Time Alerts | Error spikes, RLS violations, unauthorized access | Sentry + CloudWatch | Active
Security Events | Failed logins, role changes, exports | CloudWatch + Sentry | Tracked

## 9. Implementation Checklist
WEEK-BY-WEEK IMPLEMENTATION CHECKLIST
Week | Item | Task Details | Owner | Due Date | Status | Notes
Week 1 | AWS Account | Create + activate startup credits | Nermeen | Feb 3 | TODO
Week 1 | GitHub Setup | Create org + 3 repos + branch protection | Nermeen | Feb 4 | TODO
Week 1 | RDS/Redis | Provision + security groups configured | Nermeen | Feb 5 | TODO
Week 1 | Cognito | User Pool + app client + MFA enabled | Nermeen | Feb 6 | TODO
Week 1 | Monitoring | CloudWatch log groups + alarms created | Nermeen | Feb 7 | TODO
Week 2 | Database Schema | All 9 tables created + indexed | Nermeen | Feb 9 | TODO | RLS policies tested
Week 2 | Migrations | Migration system working (Knex/Flyway) | Nermeen | Feb 10 | TODO
Week 2 | Seed Data | 6 modules loaded + assessment template | Nermeen | Feb 11 | TODO
Week 3 | Auth Endpoints | signup, login, refresh, me complete + tested | Nermeen | Feb 15 | TODO
Week 3 | Assessment Endpoints | create, get, update, results complete | Nermeen | Feb 15 | TODO
Week 4 | Learning Endpoints | modules, progress endpoints complete | Nermeen | Feb 22 | TODO
Week 4 | Dashboard Endpoints | employee + HR views complete | Nermeen | Feb 22 | TODO
Week 4 | Email Service | SES integration + templates working | Nermeen | Feb 22 | TODO
Week 5 | Frontend Setup | React + TypeScript + Vite configured | FE Dev | Mar 8 | TODO
Week 5-6 | Auth UI | Login, signup, password reset forms | FE Dev | Mar 8 | TODO
Week 5-6 | Assessment UI | Questionnaire form + results display | FE Dev | Mar 8 | TODO
Week 5-6 | Learning UI | Module viewer + progress bar | FE Dev | Mar 15 | TODO
Week 6 | Dashboards | Employee + HR views complete | FE Dev | Mar 15 | TODO
Week 7 | E2E Testing | All user flows tested end-to-end | Both | Mar 22 | TODO | Selenium/Playwright
Week 7 | Performance | Load testing 1000 concurrent users | Nermeen | Mar 22 | TODO | P95 latency <500ms
Week 7 | Security Audit | OWASP Top 10 check + RLS validation | Nermeen | Mar 22 | TODO
Week 8 | Staging Deploy | Deploy to staging environment | Nermeen | Mar 23 | TODO
Week 8 | Smoke Tests | All endpoints respond + no errors | Both | Mar 24 | TODO
Week 8 | Documentation | README + API docs + runbook | Nermeen | Mar 25 | TODO
Week 8 | Team Training | Team trained on deploy/monitor/debug | Nermeen | Mar 26 | TODO
Week 8 | Prod Deploy | Deploy to production | Nermeen | Mar 27 | TODO | Approval from Niki
Week 8 | Customer Onboard | First pilot customer onboarded + using | Niki + Nermeen | Mar 30 | TODO | Success = 1 completed assessment

## 10. Cost & Revenue
FINANCIAL PROJECTIONS & COST BREAKDOWN
Development Costs (One-Time)
Role | Hours | Rate/Hour | Total
Phase 1: Nermeen Backend | 400 | $70 | $28,000
Phase 1: Frontend Dev | 200 | $50 | $10,000
Phase 1 Subtotal |  |  | $38,000
Phase 2: Nermeen | 300 | $70 | $21,000
Phase 2: Frontend Dev | 150 | $50 | $7,500
Phase 2: QA | 50 | $40 | $2,000
Phase 2 Subtotal |  |  | $30,500
Phase 3: Nermeen | 250 | $70 | $17,500
Phase 3: Frontend Dev | 150 | $50 | $7,500
Phase 3: Data Science | 100 | $60 | $6,000
Phase 3 Subtotal |  |  | $31,000
TOTAL (1,600 hours) |  |  | $99,500
Infrastructure Costs (Monthly, Recurring)
Service | MVP (0-1K users) | Scale (1-5K) | Enterprise (5K-10K)
Lambda | $15 | $50 | $150
RDS | $200 | $400 | $800
ElastiCache | $50 | $100 | $300
S3 + CloudFront | $20 | $30 | $50
Cognito | $5 | $10 | $10
SES | $5 | $5 | $5
CloudWatch/Monitoring | $20 | $30 | $50
Misc (KMS, Secrets, etc) | $30 | $50 | $100
TOTAL/MONTH | $345 | $675 | $1,465
Revenue Projections
Period | Customers | Avg Employees | Price/Employee/Year | Monthly | Note
Q1 2026 | 1 | 500 | $2,600 | $108 | Pilot phase
Q2 2026 | 3 | 400 | $2,600 | $2,600 | 3 customers live
Q3 2026 | 5 | 350 | $2,600 | $4,542 | Steady growth
Q4 2026 | 5 | 375 | $2,600 | $4,844 | Year-end
Year 1 Total ARR |  |  |  | $50,000 | Conservative
Year 2 Q1 | 8 | 400 | $2,600 | $6,933 | Accelerating
Year 2 Full Year | 15 | 350 | $2,600 | $11,375 | $180K+ ARR
Year 3 Target | 25-30 | 350-400 | $2,600 | $22,917 | $280K-400K ARR
Year 1 Total Cost Summary
Item | Cost
Development (3 phases) | $99,500
Infrastructure (12 months) | $5,000
Tools & Services | $2,000
TOTAL | $106,500
AWS Startup Credits | -$100,000
NET OUT-OF-POCKET | $6,500